## Survey Calendar
Optimal
| Sub-optimal | Survey Calendar
|  | Jan | Feb | Mar | Apr |  | May | Jun |  | Jul | Aug | Sep | Oct | Nov | Dec
Phase 1 habitat & hedgerow
NVC/Botanical | bar: Jul to Sep
Badger
Bats: daytime assessment |  | Some field signs may not be present all year round
roost and activity |  |  |  |  | TR only |  | Maternity/Summer roost |  |  | Sep: SR and TR; Oct: TR only
hibernation | bar: Nov to Dec
Birds: breeding | bar: Jul to Sep
wintering and migrant | bar: Sep to Dec
Dormouse |  | Nut search only |  |  | Nest only |  |  |  |  | Aug: Nest and nut search; Dec: Nut
Great crested newt: HSI
pond | [5 empty] | 2 out of 4/6 |  |  | Less effective methods may be possible | bar: Jul to Oct
Otter |  | Some field signs may not be present all year round.
Pine marten
Red squirrel |  | Survey can be undertaken throughout the year but optimum month depend on survey objectives.
Reptiles | bar: Jul to Oct
Water vole
White-clawed crayfish | bar: Jul to Oct
Note: Surveys need to be undertaken under suitable weather conditions for the species surveyed
SR: Summer roost
TR: Transitional roost

## Mitigation and Work Calendar
Recommended
| Sub-optimal | Mitigation and Work Calendar
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Hedgerow (planting)
Habitat creation |  | Depending on habitats to be created
Badger |  | Highly unlikely | [6 empty] | Under exclusion licence
Bats: maternity roost work |  | Under licence | [8 empty] | Under licence
winter roost work | [5 empty] | Under licence
Bird (nesting) |  |  |  | If absence of nest has been confirmed only
Dormouse |  | Minor work under licence
Great crested newt |  | Work under licence |  | Translocation - ponds and/or land under licence
Otter (holt closure) |  | Site specific and under licence.
Pine marten
Red squirrel (den closure) |  | Avoid habitat management in areas where red squirrels are breeding.
Reptiles |  |  |  | Translocation
Water vole |  |  |  | Translocation
White-clawed crayfish | [7 empty] | Exclusion.